## Sheet1
Phased Project Plan
Phase Num | Phase Name | Headlines | Technical steps | Resbonsible | Duration | Status | Status phase | comments
1 | Hub Virtual Network | Objectives | Establish primary hub network in Italy North |  | 1-2 Days | Done | ✅ COMPLETED
|  |  | Deploy Azure Firewall for centralized security |  | 1-2 Days | Done
|  |  | Configure GatewaySubnet for future VPN |  | 1-2 Days | Done
|  | Deliverables | vnet-erp-hub-italynorth 10.0.0.0/16 |  | 1-2 Days | Created
|  |  | GatewaySubnet 10.0.1.0/27 |  | 1-2 Days | Created
|  |  | AzureFirewallSubnet 10.0.2.0/26 |  | 1-2 Days | Created
|  |  | fw-erp-italynorth Standard SKU |  | 1-2 Days | Deployed
|  |  | Public IP (Firewall) 4.232.185.51 |  | 1-2 Days | Allocated
|  | Dependencies | Azure Subscription |  |  | Done
|  |  | Resource Group created |  |  | Done
|  |  | Network Contributor permissions |  |  | Done
|  | Validation Checklist | VNet created with correct address space |  |  | Done
|  |  | Firewall deployed and responding |  |  | Done
|  |  | Public IP assigned |  |  | Done
|  |  | Firewall policy attached |  |  | Done
2 | Spoke Virtual Networks | Objectives | Create spoke VNets for workload segregation |  | 1-2 Days | Done | ✅ COMPLETED
|  |  | Establish hub-spoke peering |  | 1-2 Days | Done
|  |  | Deploy route tables for firewall inspection |  | 1-2 Days | Done
|  | Deliverables | vnet-erp-spoke-db-italynorth 10.1.0.0/16 |  | 1-2 Days | Created
|  |  | vnet-erp-spoke-app-italynorth 10.2.0.0/16 |  | 1-2 Days | Created
|  |  | vnet-erp-spoke-storage-italynorth 10.3.0.0/16 |  | 1-2 Days | Created
|  |  | Hub-to-Spoke Peerings 3 bidirectional |  | 1-2 Days | Configured
|  |  | Route Tables Traffic to firewall |  | 1-2 Days | Applied
|  | Network Peering Matrix | Hub → Spoke |  | Gateway Transit
|  |  | hub-to-db |  | Enabled
|  |  | hub-to-app |  | Enabled
|  |  | hub-to-storage |  | Enabled
Spoke → Hub
|  |  | db-to-hub |  | Enabled
|  |  | app-to-hub |  | Enabled
|  |  | storage-to-hub |  | Enabled
|  | Validation Checklist | All spoke VNets created |  |  | Done
|  |  | Peerings in Connected state |  |  | Done
|  |  | Route tables forcing traffic to 10.0.2.4 |  |  | Done
|  |  | Gateway transit configured |  |  | Done
3 \ 6 | Infrastructure Components | Objectives | Deploy SQL Server VM in database spoke |  | Variable | Done | ✅ COMPLETED
|  |  | Deploy IIS Web Server VM in application spoke |  | Variable | Done
|  |  | Configure network security groups |  | Variable | Done
|  |  | Install and configure applications |  | Variable | Done
|  | Deliverables | vm-sql-erp-italynorth DB B2als_v2, SQL 2022 |  | Variable | Deployed
|  |  | vm-web-erp-italynorth App B2als_v2, IIS + Flask |  | Variable | Deployed
|  |  | nsg-sql-italynorth DB SQL + RDP rules |  | Variable | Applied
|  |  | nsg-web-italynorth App HTTP/HTTPS + RDP |  | Variable | Applied
Variable
|  | VM Configuration Details SQL Server VM | OS: Windows Server 2022 |  | Variable | Attatched
|  |  | SQL: SQL Server 2022 Developer |  | Variable | installed
|  |  | IP: 10.1.1.4 (Static) |  | Variable | Allocated
|  |  | Disks: OS 128GB P10 |  | Variable | Attatched
|  |  | Apps: SSMS, SQL Agent |  | Variable | installed
|  | VM Configuration Details Web Server VM | OS: Windows Server 2022 |  | Variable | Attatched
|  |  | IIS: Version 10 |  | Variable | installed
|  |  | IP: 10.2.1.4 (Static) |  | Variable | Allocated
|  |  | Apps: Python 3.11, Flask |  | Variable | Applied
|  |  | Site: Pizza Tracker Demo |  | Variable | Applied
|  | Validation Checklist | VMs accessible via RDP (through VPN) |  |  | Done
|  |  | SQL Server accepting connections on 1433 |  |  | Done
|  |  | IIS responding on port 80 |  |  | Done
|  |  | Flask application running |  |  | Done
|  |  | Database connectivity from web tier |  |  | Done
7 | Point-to-Site VPN | Objectives | Deploy VPN Gateway for remote access |  | 2-3 Days | Deployed | ✅ COMPLETED
|  |  | Configure P2S with certificate authentication |  | 2-3 Days | Deployed
|  |  | Enable secure admin access to all resources |  | 2-3 Days | Enabled
|  | Deliverables | vpngw-erp-italynorth VpnGw1, Gen1 |  | 2-3 Days | Deployed
|  |  | P2S Configuration IKEv2 + SSTP |  | 2-3 Days | Configured
|  |  | Client Address Pool 172.16.0.0/24 |  | 2-3 Days | Assigned
|  |  | Root Certificate Uploaded to Azure |  | 2-3 Days | Installed
|  |  | Client Certificate Generated |  | 2-3 Days | Distributed
|  | VPN Client Setup | Server: <gateway-public-ip> |  | 2-3 Days | Done
|  |  | Tunnel Type: IKEv2 (preferred) or SSTP |  | 2-3 Days | Done
|  |  | Authentication: Certificate |  | 2-3 Days | Done
|  |  | Client IP Range: 172.16.0.x |  | 2-3 Days | Done
|  |  | Routes: 10.0.0.0/8 via VPN |  | 2-3 Days | Done
|  | Validation Checklist | VPN Gateway provisioned (~30 min) |  |  | Done
|  |  | P2S configuration applied |  |  | Done
|  |  | Root certificate uploaded |  |  | Done
|  |  | Client can connect and get 172.16.0.x IP |  |  | Done
|  |  | RDP to VMs working through VPN |  |  | Done
8 | Azure Firewall Rules | Objectives | Configure DNAT rules for inbound traffic |  | 1 Day | Done | ✅ COMPLETED
|  |  | Configure application rules for outbound filtering |  | 1 Day | Done
|  |  | Block social media (YouTube demo) |  | 1 Day | Done
|  | Deliverables | DNAT Allow-HTTP-to-Web Internet → 10.2.1.4:80 |  |  | Active
|  |  | Network Allow-Internal 10.0.0.0/8 ↔ 10.0.0.0/8 |  |  | Active
|  |  | Network Allow-DNS All → 168.63.129.16:53 |  |  | Active
|  |  | Application Allow-Azure HTTPS to *.azure.com |  |  | Active
|  |  | Application Block-YouTube Deny *.youtube.com |  |  | Active
|  | Firewall Policy Structure "Firewall Policy" | DNAT Rules Collection (Priority: 100) Allow-HTTP-to-Web |  | 1 Day | Done
|  |  | Network Rules Collection (Priority: 200) Allow-Internal Allow-DNS Allow-KMS |  | 1 Day | Done
|  |  | Application Rules Collection (Priority: 300) Allow-Azure-Services Allow-Windows-Update Deny-Social-Media |  | 1 Day | Done
|  | Validation Checklist | HTTP traffic reaches web VM through firewall |  |  | Done
|  |  | YouTube blocked when accessed from VMs |  |  | Done
|  |  | Windows Update works |  |  | Done
|  |  | Azure services accessible |  |  | Done
9 | Azure Front Door | Objectives | Deploy global load balancer with WAF |  | 1-2 Days |  | ✅ COMPLETED
|  |  | Configure origin groups for failover |  | 1-2 Days
|  |  | Enable CDN caching for static content |  | 1-2 Days
|  | Deliverables | fd-erp-manufacturing Standard tier |  | 1-2 Days | Deployed
|  |  | Endpoint erp-frontend-*.azurefd.net |  | 1-2 Days | Active
|  |  | Origin Group og-erp-primary |  | 1-2 Days | Configured
|  |  | Primary Origin 4.232.185.51 (Priority 1) |  | 1-2 Days | Healthy
|  |  | DR Origin 4.210.68.185 (Priority 2) |  | 1-2 Days | Healthy
|  |  | WAF Policy OWASP 3.2, Prevention |  | 1-2 Days | Applied
|  | Front Door Architecture | 1- Users (Global)
2- │Azure Front │ │ Door + WAF │ │ + CDN Cache │
3-Primary Origin (Priority 1)
4-DR Origin (Priority 2)
|  | Validation Checklist | Front Door endpoint accessible |  |  | Done
|  |  | Traffic routed to primary origin |  |  | Done
|  |  | WAF blocking malicious requests |  |  | Done
|  |  | Origin health probes passing |  |  | Done
|  |  | DR origin configured for failover |  |  | Done
Done
10 | Azure Site Recovery | Objectives | Deploy Recovery Services Vault in DR region |  | 2-3 Days |  | ✅ COMPLETED
|  |  | Configure VM replication to North Europe |  | 2-3 Days
|  |  | Set RPO/RTO targets |  | 2-3 Days
|  | Deliverables | rsv-erp-dr-northeurope North Europe |  | 2-3 Days | Deployed
|  |  | SQL VM Replication Italy North → North Europe |  | 2-3 Days | Replicating
|  |  | Web VM Replication Italy North → North Europe |  | 2-3 Days | Replicating
|  |  | Replication Policy 15 min RPO |  | 2-3 Days | Applied
|  |  | Recovery Plans erp-recovery-plan |  | 2-3 Days | Created
|  | ASR Configuration | Recovery Services Vault
|  |  | Replicated Items vm-sql-erp-italynorth → vm-sql-erp-italynorth-replica vm-web-erp-italynorth → vm-web-erp-italynorth-replica |  | 2-3 Days | Done
|  |  | Replication Policy RPO: 15 minutes Recovery Points: 24 hours App-consistent: 4 hours |  | 24 hours | Done
|  |  | Recovery Plans erp-recovery-plan (SQL first, then Web) |  | 2-3 Days | Done
|  | Validation Checklist | Vault created in North Europe |  |  | Done
|  |  | Both VMs showing “Protected” |  |  | Done
|  |  | Initial replication completed |  |  | Done
|  |  | Recovery plan tested (Test Failover) |  |  | Done
|  |  | Failover network mappings configured |  |  | Done
12 | DR Virtual Machines | Objectives | Test failover to DR region |  | 1 Day | Done | ✅ COMPLETED
|  |  | Validate replica VM functionality |  | 1 Day | Done
|  |  | Configure DR network settings |  | 1 Day | Done
|  | Deliverables | vm-sql-erp-italynorth-replica North Europe |  | 1 Day | Available
|  |  | vm-web-erp-italynorth-replica North Europe |  | 1 Day | Available
|  |  | vnet-erp-spoke-db-italynorth-asr 10.11.0.0/16 |  | 1 Day | Created
|  |  | vnet-erp-spoke-app-italynorth-asr 10.12.0.0/16 |  | 1 Day | Created
|  | Validation Checklist | Test failover successful |  |  | Done
|  |  | Replica VMs boot and function |  |  | Done
|  |  | Application accessible in DR |  |  | Done
|  |  | Database connectivity verified |  |  | Done
13 | DR Hub Infrastructure | Objectives | Deploy DR hub network in North Europe |  | 1-2 Days | Done | ✅ COMPLETED
|  |  | Deploy DR Azure Firewall |  | 1-2 Days | Done
|  |  | Configure hub-to-spoke peerings in DR |  | 1-2 Days | Done
|  |  | Update Front Door with DR origin |  | 1-2 Days | Done
|  | Deliverables | rg-erp-hub-dr-northeurope North Europe |  | 1-2 Days | Created
|  |  | vnet-erp-hub-dr-northeurope 10.10.0.0/16 |  | 1-2 Days | Created
|  |  | GatewaySubnet 10.10.1.0/27 |  | 1-2 Days | Created
|  |  | AzureFirewallSubnet 10.10.2.0/26 |  | 1-2 Days | Created
|  |  | fw-erp-dr-northeurope Standard SKU |  | 1-2 Days | Deployed
|  |  | Public IP (DR FW) 4.210.68.185 |  | 1-2 Days | Allocated
|  |  | Hub-to-Spoke Peerings DB + App ASR VNets |  | 1-2 Days | Configured
|  |  | Route Tables Traffic to 10.10.2.4 |  | 1-2 Days | Applied
|  |  | Firewall Rules Mirror of primary |  | 1-2 Days | Configured
|  |  | Front Door DR Origin Priority 2 |  | 1-2 Days | Added
|  | DR Network Architecture | North Europe (DR Region)
|  |  | Hub VNet (10.10.0.0/16) 1-GatewaySubnet (10.10.1.0/27) 2-AzureFirewallSubnet (10.10.2.0/26) 2.1-fw-erp-dr-northeurope (10.10.2.4) 3-snet-management (10.10.3.0/24) |  |  | Created
|  |  | Peering: hub-dr-to-spoke-db-asr |  |  | Created
|  |  | Peering: hub-dr-to-spoke-app-asr |  |  | Created
|  |  | Route Tables: rt-dr-spoke-to-firewall |  |  | Created
|  | Validation Checklist | DR hub VNet created |  |  | Done
|  |  | DR firewall deployed and healthy |  |  | Done
|  |  | Hub-to-spoke peerings connected |  |  | Done
|  |  | Route tables forcing traffic to DR firewall |  |  | Done
|  |  | DNAT rule allowing HTTP to DR web VM |  |  | Done
|  |  | Front Door health probes passing to DR origin |  |  | Done
|  |  | End-to-end DR failover tested |  |  | Done